## Level 1 Operational
Reconstitution Level 1 (Operational Planning)
Listed below are the preparedness activities and actions to be conducted for returning operations to the primary operating facility.
● | Plans and Procedures:
Develop a building assessment checklist.
Identify location of classified materials.
Identify location of essential records storage areas.
Develop equipment recovery and salvage plan/checklist.
Develop information and instructions to organization personnel on when and how to to resume normal operations.
Develop personnel utilization plan. Based on the assessment results, personnel may be asked to telework, if that is a viable capability. Some personnel may need to be relocated to another region, district, or office to work. Some agencies or departments may chose to perform shiftwork at the continuity facility instead of putting personnel on administrative leave.
Develop plans and procedures to utilize telework as a Reconstitution strategy.
Develop procedures on how to account for organization personnel.
Develop a contact list for key personnel internal and external to the [Organization Name].
Develop procedures for supervising an orderly move to the primary operating facility.
Develop procedures for resuming operations at the primary operating facility.
Develop procedures to verify all systems, communications, essential records, infrastructure, and required capabilities are available and operational.
Develop reporting and communications requirements operating procedures
Develop guidance and provide training for developing the Continuity Status Report (CSR) on reconstitution status.
Develop guidance for conducting the after action review and developing the after action report/improvement plan (AAR/IP).
Develop and document Level 1 Reconstitution Planning Team operating procedures.
Establish and document a process for assessing the status of primary operating facility.
Establish and document Level 1 space requirements.
Establish and document a priority-based phased approach to Reconstitution.
● | Personnel/Staff:
Identify a Reconstitution Manager
Identify Reconstitution Planning Team members
Identify potential Reconstitution Team Members
Develop and train a building assessment team
Reference: FEMA, Reconstitution Plan Template, Sept. 2014, pgs. 3-2 to 3-4

## Level 2 Short Term
Reconstitution Level 2 (Short Term Planning)
Listed below are the preparedness activities and actions to be conducted for moving operations to a temporary operating facility. Listed below are the preparedness activities and actions to be conducted for moving operations to a temporary operating facility.
● | Plans and Procedures:
Develop a building assessment checklist.
Identify location of classified materials.
Identify location of vital records storage areas.
Develop equipment recovery and salvage checklist/plan.
Develop information and instructions to organization personnel on when and how to
resume normal operations.
Develop procedures on how to account for organization personnel.
Develop a contact list for key personnel internal and external to the [Organization Name].
Develop procedures for supervising an orderly move to the temporary operating facility.
Develop procedures for resuming operations at the temporary operating facility.
Develop procedures to verify all systems, communications, and required capabilities are
available and operational.
Develop reporting and communications requirements operating procedures.
Develop guidance and provide training for developing the Continuity Status Report (CSR)
on reconstitution status.
Develop guidance for conducting the after action review and developing the after action
report/improvement plan (AAR/IP).
Develop and document Level 2 Reconstitution Planning Team operating procedures.
Establish and document a process for assessing the status of primary operating facility.
Establish and document a process for assessing the status of temporary operating facility.
Establish and document Level 2 space requirements.
Establish and document a priority-based phased approach to reconstitution.
● | Personnel/Staff:
Identify a Reconstitution Manager
Identify Reconstitution Planning Team members
Identify potential Reconstitution Team Members
Develop and train a building assessment team
Reference: FEMA, Reconstitution Plan Template, Sept. 2014, pgs. 3-2 to 3-4

## Level 3 Long Term
Reconstitution Level 3 (Long-Term Planning)
Listed below are the preparedness activities and actions to be conducted for moving operations to a new or rebuilt operating facility.
● | Plans and Procedures:
Develop a building assessment checklist.
Identify location of classified materials.
Identify location of essential records storage areas.
Develop equipment recovery and salvage checklist/plan.
Develop information and instructions to organization personnel on when and how to
resume normal operations.
Develop procedures on how to account for organization personnel.
Develop a contact list for key personnel internal and external to the [Organization Name].
Develop procedures for supervising an orderly move to a new/restored facility.
Develop procedures for resuming operations at a new/restored facility.
Develop procedures to verify all systems, communications, and required capabilities are
available and operational.
Develop reporting and communications requirements operating procedures.
Develop guidance and provide training for developing the Continuity Status Report (CSR)
on reconstitution status.
Develop guidance for conducting the after action review and developing the after action
report/improvement plan (AAR/IP).
Develop Level 3 Reconstitution Planning Team operating procedures.
Establish and document a process for assessing the status of the affected facility.
Establish and document Level 3 space requirements.
Establish and document a priority-based phased approach to reconstitution.
● | Personnel/Staff:
Identify a Reconstitution Manager
Identify Reconstitution Planning Team members
Identify potential Reconstitution Team Members
Develop and train a building assessment team
Reference: FEMA, Reconstitution Plan Template, Sept. 2014, pgs. 3-2 to 3-4