## Introduction
MILESTONE LIST INTRODUCTION
Click on a Section Name to go directly to that Section. Otherwise select the RED TAB labeled "Milestone List" at the bottom of the page for the complete Milestone List. Red star means Senior Leadership decision is required.
LIST OF SECTIONS:
START PLANNING
ESSENTIAL FUNCTIONS
EMERGENCY RELOCATION GROUP (ERG)
BUSINESS PROCESS ANALYSIS (BPA)
BUSINESS IMPACT ANALYSIS (BIA)
RISK MITIGATION EVALUATION
CONTINUITY FACILITIES
DEVOLUTION
CONTINUITY COMMUNICATIONS
ESSENTIAL RECORDS MANAGEMENT
ORDERS OF SUCCESSION
DELEGATIONS OF AUTHORITY
HUMAN RESOURCES
BUDGETING & ACQUISITION OF RESOURCES
RECONSTITUTION
TRAINING, TESTING AND EVALUATION
FINAL PLAN COORDINATION
PLAN SUSTAINMENT
Download CGC-1 and CGC-2 | Continuity Guidance Circular 1 (CGC 1)
for your referance: | Continuity Guidance Circular 2 (CGC 2)
List of FEMA classes for Level I: | FEMA CLASSES for Level 1 and 2 Continuity Practicioner

## Milestone List
(Insert Agency Name) Continuity of Operations Plan Milestones
NO. | Target Date | Action | Person(s) Responsible | Notes | Status
START PLANNING
|  | Initial Research. | Continuity Planner | Check the following: 1. Statutes, laws, executive orders, or directives that charge the organization with responsibility to perform missions; 2. Mission statements that describe the overarching mission(s) or list the services provided by the organization 3. The organization’s strategic plan 4. Published organization literature; and/or Interviews with organization leadership and external partners
|  | Develop/Amend Milestones | Continuity Planner | Add Target Dates Tailor Milestones to the Agency
|  | Schedule initial interview with Senior Leadership (Agency Directors) - Determine best dates to conduct each department/section interviews | Continuity Planner and Senior Leadership | Prepare presentation: - Get leadership buy-in - Explain recommended course of action (Milestones) - Identify needed leadership decisions
|  | Format DRAFT Agency COOP Plan | Continuity Planner | In accordance with FEMA Templates - COOP Basic - Devolution - Telework - Reconstitution - Pandemic Influenza COOP Annex
COOP Plan template (WORD)
COOP Plan template and instructions (WORD)
|  | Meeting with Section/Department leaders | Continuity Planner and Section/Dept. Chiefs and Managers | Provide plan overview and interview questions
|  | Schedule meeting with IT representatives | Continuity Planner and IT | Provide an overview of the planning process, initial questions can include: - Location of main and backup servers - Ability to access from alternate work sites - Access to essential records - Access to software/applications that support Essential Functions - Emergency Communications
|  | Schedule one-on-one meeting with Section/Department Chiefs | Continuity Planner and Section/Dept. Chiefs | Send e-mail describing process to determine Essential Functions with the Candidate MEF Worksheet so they can list all their functions before meeting
ESSENTIAL FUNCTIONS
|  | STEP 1. Identify Organizational Functions. List all functions per each Department. Section/Department Chiefs can do this on the Candidate MEF Worksheet that was emailed to them. | Section/Dept. Chiefs and Managers | Candidate MEF Worksheet (Excel)
|  | STEP 2. Identify Possible Mission Essential Functions. | Section/Dept. Chiefs and Managers and Continuity Planner | From the Candidate MEF Worksheet, determine what functions are: - Texas Essential Functions; - Primary Mission Essential Functions (PMEFs): - Mission Essential Functions (MEFs); and - Essential Support Activity (ESA). The Candidate MEF Worksheet will help in listing all Functions and determine what are PMEFs, MEFs and Essential Supporting Activities (ESA). (Use all identified Essential Functions for the MEF Data Sheet. Because you have collected all functions, use this information for Reconstitution)
|  | STEP 3. Develop MEF Data Sheets Conduct a detailed review of each MEF and document the information on the MEF Data Sheet | Section/Dept. Chiefs and Managers and Continuity Planner | MEF Data Sheet template (use for each MEF)
|  | STEP 4. Prioritize Identified MEFs. If resources are limited, an organization may have to focus its attention on some MEFs before others. | Section/Dept. Chiefs and Managers and ERG Leaders with the Continuity Planner | Several factors are necessary to include in the MEF prioritization determination, including the following: 1. Recovery Time Objective: The MEF data sheet identifies the required recovery time for each MEF. Those MEFs that must be continuously performed or those with the shortest recovery times will generally be given priority over MEFs with longer recovery times. 2. Impacts If Not Conducted: The impact of not conducting or delaying the performance of each MEF would be part of the prioritization determination. 3. Management Priority: Some missions will have a higher priority as a result of management preference and discretion.
|  | STEP 5. Submit The Identified MEFs for Leadership Approval. | Senior Leadership | Obtain senior organizational leaders’ or elected officials’ review, validation, and approval of the MEFs, MEF descriptions, and MEF prioritization.
EMERGENCY RELOCATION GROUP (ERG)
|  | Develop Presentation: Emergency Relocation Group Mission, Roles and Responsibilities | Continuity Planner | Purpose is to outline the role, responsibilities of the ERG Team, criteria to consider in the selection of its leader, members, and alternates
|  | Meeting with Section/Department leaders | Continuity Planner | Provide ERG Presentation Discuss ERG makeup Recommendations as to ERG Team Leader and members
|  | Select ERG Leader | Section/Dept. Chiefs and Managers | Based on Essential Function determination, appoint Emergency Relocation Group Leader (ERG Leader)
|  | Select ERG Team and alternates | Section/Dept. Chiefs and Managers | ERG Leader will select ERG Team required to perform essential functions § ERG Leader will fill out MEF Data Sheet
|  | Notify ERG members and alternates in writing | Designated Agency Leader | ERG Notification Letter template (WORD)
|  | Meet with ERG Team | Continuity Planner | § Provide presentation on ERG Team mission, roles, and responsibilities § Collect data necessary to perform their MEFs - Verify that maintenance strategies for communications and vital records and databases have been established - Identify essential records and data required to support their essential function - Identify mission-critical systems required to support essential functions - List what they will need for their drive-away kit and where it will be stored.
|  | Write ERG activation procedures | Designated Agency Leader with Continuity Planner | · Develop alert notification procedures · Develop telephone tree · Designate what personnel will enter building (if deemed safe) to salvage essential equipment and supplies
|  | Recommend the content and maintenance of Drive-Away Kits for ERG members | ERG Leader with Continuity Planner | SAMPLE Drive-Away Kit template (WORD)
|  | Provide guidance to ERG members on individual preparedness measures they should take to ensure response to a continuity activation | Continuity Planner and ERG Leader | Read CGC-1; ANNEX J-2 "Considerations for Human Resources" for more information on what guidance to provide ERG and DERG members.
BUSINESS PROCESS ANALYSIS (BPA)
|  | Once Candidate Mission Essential Functions are approved and the ERG Leader is selected, the Business Process Analysis (BPA) can be initiated. |  | BPA Data Sheet template (WORD)
|  | STEP 1. Identify MEF Output. | Section/Dept. Chiefs and Managers facilitated by Continuity Planner | The MEF outputs align with and expand on details in the MEF Descriptive Narrative as documented on the MEF Data Sheet
|  | STEP 2. Identify Input Requirements. | Section/Dept. Chiefs and Managers facilitated by Continuity Planner | The input may be required at the beginning of the process, or as the process proceeds. Specific information includes input supplier (i.e., organization, partner, etc.) and delivery time requirements.
|  | STEP 3. Identify Leadership who Perform the MEF. | Section/Dept. Chiefs and Managers facilitated by Continuity Planner | Leadership includes the most senior leaders as opposed to mid-level and office managers. Some MEFs require specific senior decision making; therefore, the specific involvement of leadership will be identified (e.g., the Police Commissioner must authorize the use of special security tactics during an emergency).
|  | STEP 4. Identify Staff who Perform and Support the MEF. | Section/Dept. Chiefs and Managers facilitated by Continuity Planner | The specific skill sets, expertise, and authorities required to support and perform each function (both the MEF and the ESA) should be identified.
|  | STEP 5. Identify, Communications & Information Technology Requirements. | Section/Dept. Chiefs and Managers | What communications and information technology (IT) software and equipment are required to support MEF performance.
|  | STEP 6. Identify Facilities Requirements. | Section/Dept. Chiefs and Managers facilitated by Continuity Planner | What are the facility requirements for performing the MEF Some examples of facility requirements are: Dedicated work space - Square footage - Number of telephones - Electrical Outlets - Internet and Network Access - Access to photocopy equipment Parking Lodging Food Services Medical Support Unique security requirements - Keys and access badges - Vendor access
|  | STEP 7. Identify Resources and Budgeting Requirements. | Section/Dept. Chiefs and Managers facilitated by Continuity Planner | What supplies, services, capabilities (not already addressed) are required to perform the MEF? What are the funding sources? Requirements not identified elsewhere can be included in Step 7.
|  | STEP 8. Identify Partners and Interdependencies. Who are the internal/external organizations that support/ensure MEF performance, and what information, supplies, equipment, or products do they provide? | Section/Dept. Chiefs and Managers facilitated by Continuity Planner | Example of information to include for each interdependent relationship: 1. Organization name; 2. Point of contact and contact information; 3. Types of information, data, services, and support provided; 4. Coordination requirements; 5. Timelines and due dates, as appropriate. Note: An important element to consider is whether the partners understand their input is necessary for another organization’s performance of an essential function. Has that partner made plans to be able to provide that critical input during a disruption? Is a Memorandum of Agreement necessary and in place?
|  | STEP 9. Describe Process Flow. | Section/Dept. Chiefs and Managers facilitated by Continuity Planner | From start to finish, determine how the MEF is performed. A description of the procedures and process details capture the specifics of how the MEF is performed by addressing the following questions: 1. What initiates performance of the MEF? 2. What inputs are required to perform the MEF? 3. When are the inputs needed and where do they come from? 4. What people, facilities, resources, partners, and communications are required to support and perform the MEF? 5. What processes are employed to perform the MEF? 6. What are the MEF outputs or desired outcomes? 7. What aspect(s) of the MEF could be supported through telework or another remote arrangement(s)?
BUSINESS IMPACT ANALYSIS (BIA)
|  | Conduct a Business Impact Analysis | Continuity Planner | Create interview questionnaires for each department in order to facilitate agency’s Business Impact Analysis (BIA)
|  | Obtain copy of Threat and Hazard Identification Risk Assessment (THIRA) for the jurisdiction in which the agency is located | Continuity Planner | In the Austin area, contact the City of Austin Office of Emergency Management for their THIRA.
|  | STEP 1. Identify Potential Threats and Hazards. What threats and hazards could interrupt MEF performance? | Section/Dept. Chiefs and Managers facilitated by Continuity Planner | Business Impact Analysis (BIA) Worksheet template (Excel)
|  | STEP 2. Identify Threat and Hazard Characteristics. | Continuity Planner | Potential Threats and Hazards Table (Word)
|  | STEP 3. Estimate Likelihood of Threat or Hazard Occurrence. What is the likelihood each threat or hazard could occur and affect MEF performance? | Continuity Planner | Likelihood of Threat or Hazard Occurrence Table
|  | STEP 4. Evaluate MEF Vulnerability to Each Threat or Hazard. How susceptible is the MEF to failure due to each threat or hazard? | Section/Dept. Chiefs and Managers facilitated by Continuity Planner | MEF Vulnerability Values Table
|  | STEP 5. Estimate Overall Impact of MEF Failure. How significant is the impact if the MEF cannot be performed? | Section/Dept. Chiefs and Managers facilitated by Continuity Planner | MEF Failure Impact Value Table
|  | STEP 6. Determine Risk Value for Each Threat or Hazard. | Continuity Planner | Based on likelihood, vulnerability, and impact of the threat or hazard, what is the risk value for the MEF? Found from the BIA worksheet above. Formula is: Likelihood of occurrence + Vulnerability + Impact = Risk
RISK MITIGATION EVALUATION
|  | Texas state agencies are required to report to the Director of the State Office of Risk Management, the detailed information on existing and potential exposure to loss, including property location and values, descriptions of agency operations, and estimates of maximum probable and maximum possible losses by category of risk. Texas Labor Code § 412.053 | Continuity Planner | Complete the "Property Schedule/SORM 200" reporting through RMIS, the online system that SORM uses to gather data. We generate a report that will identify natural catastrophic threats specific to your geographical area and specifically to your building address. This will also fulfill the requirement TL7 (Row 266 under Risk Management) on the Texas Continuity Crosswalk.
Property Schedule/SORM 200 instructions
|  | Find your property's Latitude and Longitude for the Property Schedule. |  | https://mynasadata.larc.nasa.gov/latitudelongitude-finder/
|  | STEP 1. Evaluate Risk Mitigation Requirements and Potential Options: | Continuity Planner with Designated Agency Leadership | Review BIA results, evaluate risk value, determine risk mitigation requirements, and assess risk mitigation options.
|  | STEP 2. Identify Risk Mitigation Options and Develop Risk Mitigation Plan: Identify feasible options for reducing MEF risk and develop mitigation approach and implementation plan. | Continuity Planner with Risk Manager or designated Agency personnel | MEF Risk Mitigation Plan Template (WORD)
|  | STEP 3. Submit Risk Mitigation Plan for Leadership Approval: | Continuity Planner with Risk Manager or designated Agency personnel | MEF Risk Mitigation Plan Approval Package: 1. Executive Summary - provides an overview of the BIA process that was performed, the significance of the BIA results, and a summary of the MEF risk mitigation proposal 2. BIA Results - the overall results from the BIA to include BIA threats and hazards analysis worksheet(s) 3. Risk Mitigation Recommendations - based on MEF Risk Value, as identified in the BIA Worksheet 4. Next Steps - actions to be taken based on the plan approval 5. Additional Supporting Materials - other materials to support BIA findings and risk mitigation recommendations
STEP 4. Implement Risk Mitigation Plan:
|  | STEP 5. Assess Risk Mitigation Effectiveness: | Continuity Planner with Risk Manager or designated Agency personnel | Test, train, exercise and assess the new equipment or procedures. Initiate corrective actions if risks remain high.
CONTINUITY FACILITIES
|  | Determine requirements for suitable alternate facility during continuity events. | ERG Leader and Continuity Planner | Considerations: ● Distance from Agency ● Size of ERG Team ● Identify equipment needs ● Dedicated work space - Square footage - Number of telephones - Electrical Outlets - Internet and Network Access - Access to photocopy equipment - Parking - Lodging - Food Services - Medical Support ● Unique security requirements (keys and access badges, vendor access) ● Alert/Notification requirements - Required notification time for owner/occupant of facility to have it configured and available for occupancy ● Participation in annual exercise
|  | Identify possible hot sites, warm sites, and /or cold sites for agency. | ERG Leader and Continuity Planner | Hot site; Warm site Cold site
|  | Determine best option for alternate site for agency. | ERG Leader and Continuity Planner
|  | Alternate facility is identified | ERG Leader and Continuity Planner | Coordinate requirements with owners/agency of alternate facility (If you do not have a relationship with a facility that will fulfill your alternate site needs, go to the Texas Facilities Commission portal and submit your requirements. (TFC is now in the process of creating portal for state agencies to use for their Continuity Plans. Portal should be ready by the middle of March, 2014)
|  | DRAFT Memorandum of Agreement for alternate facility | ERG Leader and Continuity Planner | Link to: Memorandum of Agreement template
|  | Submit MOA for General Counsel Review | Senior Leadership
|  | Submit approved MOA for signatures | Leadership from Agency and Facility Host
|  | File MOA with Texas Facilities Commission |  | Texas Facilities Commission is in the process of creating a portal for Agencies' COOP Planners to submit their MOAs
DEVOLUTION
Consider the Devolution option:
|  | 1. Develop a devolution option for continuity to address how it will identify and conduct its essential functions when the primary operating facility, alternate site, and/or ERG members are not available. | Continuity Planner and ERG Leader
|  | 2. Address the following elements of a viable continuity capability in the devolution option: § risk management § budgeting and acquisitions § essential functions § orders of succession and delegations of authority specific to the devolution site § continuity communications § essential records management § human resources § Testing, Training and Exercising (TT&E) § reconstitution | Continuity Planner
|  | 3. For each identified essential function, determine the necessary resources to facilitate those functions' immediate and seamless transfer to the devolution site. | Continuity Planner and DERG Leader
|  | 4. Include a roster that identifies fully trained DERG members stationed at the designated devolution site who have the authority to perform essential functions when the devolution option of the continuity plan is activated. | Continuity Planner and DERG Leader
|  | 5. Identify what would likely activate or "trigger" the devolution option | Section/Dept. Chiefs and Managers facilitated by Continuity Planner
|  | 6. Specify how and when direction and control of organization operations will be transferred to and from the devolution site. | DERG Leader and Continuity Planner
|  | 7. List the necessary resources, such as equipment and materials, to facilitate the performance of essential functions at the devolution site. | DERG Leader and Continuity Planner
|  | 8. Establish and maintain reliable processes and procedures for acquiring the resources necessary to continue essential functions and to sustain those operations for extended periods. | DERG Leader and Continuity Planner
|  | If applicable, choose a devolution site, taking into consideration capabilities of the site to ensure it has the communications, systems, equipment and resources pre-positioned or available within the accepted timeframe to continue essential functions | DERG Leader and Continuity Planner
CONTINUITY COMMUNICATIONS
|  | Plan for the availability of robust and effective communications to provide connectivity under all conditions, among key leadership, internal elements, other organizations, critical customers, and the public. | Continuity Planner and IT | Considerations for continuity communications: In accordance with the applicable laws and guidance, and other established communications requirements: 1. (Agencies that directly support STTEFs) should possess, operate, and maintain, or have dedicated access to, communications capabilities at both their primary operating facility and continuity facility locations, as well as mobile, in-transit communications capabilities for their senior leadership, to ensure the continuation of those organizations’ essential functions across the full spectrum of hazards, threats, and emergencies, including catastrophic attacks or disasters. Secure and non-secure communications requirements should be incorporated, as applicable. 2. (Agencies that do not directly support STTEFs) should possess, operate, and maintain, or have dedicated access to, communications capabilities at both their primary operating facility and continuity facility locations, as well as mobile in-transit communications capabilities for their senior leadership capabilities, as required, to ensure the continuation of those organizations’ essential functions. Secure and non-secure communications requirements should be incorporated, as applicable. 3. Organizations who share a continuity facility with another organization should have a signed agreement with that organization to ensure each has adequate access to communications resources.
ESSENTIAL RECORDS MANAGEMENT
|  | Identify, protect and make readily available essential records, databases, and hardcopy documents needed to support essential functions | Records Manager | Considerations for essential records management: An official essential records program should: 1. Identify and protect those records that specify how an organization will operate in an emergency or disaster; 2. Identify and protect those records necessary to the organization’s continuing essential functions and resumption or normal operations; 3. Identify and protect those records needed to protect the legal and financial rights of the organization and the public; and 4. Include appropriate policies, authorities, procedures and the written designation of an essential records manager.
|  | Inventory Agency's Essential Records | Records Manager | Essential Records Inventory Template
ORDERS OF SUCCESSION
|  | Designate Agency's Orders of Succession | Senior Leadership | Considerations for Orders of Succession:
1. Establish and document orders of succession in advance and in accordance with applicable laws to ensure there is an orderly and predefined transition of leadership during any emergency
2. Establish an order of succession for the position of organization head to ensure a designated official is available to serve as acting head of the organization until that official is appointed by an appropriate authority, replaced by the permanently appointed official, or otherwise relieved.
3. Establish orders of succession for other key organization leadership positions, including, but not limited to, administrators, regional or field directors, and key managers
4. Within each order of succession, organizations should include at least three positions permitted to succeed to the identified leadership position.
5. Organizations should describe orders of succession by positions or titles, rather than by the names of the individuals holding those offices.
6. Organizations should include at least one individual in their order of succession who is geographically dispersed from the organization head and other individuals within the order of succession. All organizations should include an individual who is geographically dispersed in all HQ and non-HQ orders of succession, where feasible.
7. Organizations at all levels should coordinate the development and revision of orders of succession with their general counsel or chief counsel to ensure legal sufficiency.
8. Organizations should include orders of succession in the essential records and ensure they are available at all continuity facilities.
9. Organizations should revise orders of succession, as necessary, and distribute the revisions promptly as changes occur to higher organization authorities, potential successors, affected staff, and others, as appropriate.
|  | After designating positions and line of succession, develop (or revise) orders of succession with general counsel or chief counsel | Senior Leadership
DELEGATIONS OF AUTHORITY
|  | Establish and document agency's Delegation of Authority | Senior Leadership
|  | 1. In accordance with applicable laws, establish and document in advance the legal authority for the position of Organization Head and other key supporting positions to make key policy decisions during a continuity situation, Including: |  | a. Outline explicitly in a statement the authority, including any exceptions to that authority, of an official so designated to exercise organization direction; b. Delineate the limits of authority and accountability; c. Establish the rules and procedures designated officials must follow when facing the issues of succession to office; d. Outline the authority of officials to re-delegate functions and activities, as appropriate; e. Define the circumstances under which delegation of authorities would take effect and would be terminated; and f. Incorporate the conditions under which delegations will take place, the method of notification, the duration the delegations may last, conditions when the delegations may be terminated, and any temporal, geographical, or organizational limitations to the authorities granted by the orders of succession or delegations of authorities, including the ability to re-delegate authorities
|  | 2. Inform those officials listed within the delegations of authority who might be expected to assume authorities in a continuity activation. | Continuity Planner
|  | 3. Include delegations of authority as an essential record and ensure they are available at all continuity facilities. | Continuity Planner
|  | 4. Coordinate the development and revisions of delegations of authority with their general counsel or chief counsel to ensure legal sufficiency | Senior Leadership
HUMAN RESOURCES
|  | Develop and implement processes to identify, document, and prepare ERG members who are capable of relocating to alternate sites or teleworking and DERG members at the devolution site to support the Continuation of the performance of essential functions | Continuity Planner with Designated Leadership | a. Clearly define the expectations, roles and responsibilities of ERG and DERG members during a continuity activation; b. Establish and maintain appropriate point-of-contact rosters of trained ERG and DERG members who have the ability to perform essential functions. Organizations should update these rosters periodically and include, at a minimum, names, home, work, and cell telephone numbers; c. Ensure that ERG and DERG members are officially informed of an accept their roles and responsibilities by providing documentation to these individuals; d. Organizations should identify replacement personnel and contract workers, as necessary; and e. If bargaining unit employees are included as ERG or DERG members, organizations should ensure that all applicable collective bargaining obligations are satisfied.
|  | Provide guidance to all staff in preparing, planning and staying informed during an emergency, including developing Family Emergency Plans | Continuity Planner with Designated Leadership | Links to Family Communication Plan for child and for parent:
Family Communication Plan for children
Family Communication Plan for parents
|  | Implement a process to communicate the organization's operating status to all staff | Continuity Planner with Designated Leadership
|  | Implement a process to contact and account for all staff, including contractors, in the event of an emergency. All staff, including contractors, should know their responsibilities to report their accountability | Continuity Planner with Designated Leadership
|  | Establish procedures and provide the ability to communicate with and coordinate activities with: · all personnel; · continuity facilities and support teams; · organizations with which the affected organization interacts; customers; and · stakeholders before, during, and after a continuity event, including alert and notification. | Continuity Planner with Designated Leadership
|  | If applicable, work with labor unions in developing and bargaining over such procedure where bargaining unit employees are impacted | Continuity Planner with Designated Leadership
|  | Communicate how, and the extent to which, employees are expected to remain in contact with their agency during any closure situation | Continuity Planner with Designated Leadership
|  | Establish and maintain procedures to provide guidance to non-ERG personnel | Continuity Planner with Designated Leadership
|  | Facilitate dialogue among the Director of Human Resources, Telework Managing Officer, and Continuity Manager when developing the continuity plans | Continuity Planner with Designated Leadership
|  | Implement a process to communicate their human resources guidance for emergencies, such as pay, leave, staffing, and other human resources flexibilities, to all staff. | Continuity Planner with Designated Leadership
|  | Within continuity plans and procedures, include reference provisions and procedures for assisting all staff, especially those who are disaster survivors, with special human resources concerns following a catastrophic disaster. | Continuity Planner with Designated Leadership
|  | Continuity program, plans, and procedures should incorporate or reference existing organization-specific guidance and policy for human resource management, such as guidance on pay, leave, work scheduling, benefits, telework, hiring, authorities, and flexibilities. | Continuity Planner with Designated Leadership
BUDGETING AND ACQUISITION OF RESOURCES
|  | Identify Budgetary requirements for addressing organizational resilience and continuity interdependencies in the performance of internal and other organizations' essential functions | Continuity Planner with Designated Leadership
|  | Provide for the acquisition of those resources necessary for continuity operations on an emergency basis | Continuity Planner with Designated Leadership
|  | Consider additional continuity factors such as probabilities of occurrence, mission priorities, and impact assessments, as part of the continuity risk management methodology. | Continuity Planner with Designated Leadership | Re-evaluate your insurance policies to mitigate risk identified in your risk assessment.
RECONSTITUTION
|  | PHASE I: PREPAREDNESS - PLANNING AND PREPARING FOR RECONSTITUTION |  | FEMA Reconstitution Template (WORD)
|  | ● Develop checklists and key personnel contact lists | Continuity Planner with Designated Leadership
|  | ● Develop essential records list | Continuity Planner with Designated Leadership | Essential Records Inventory
|  | ● Develop reconstitution packet | Continuity Planner with Designated Leadership
|  | ● Identify the Reconstitution Manager and potential Reconstitution Team members | Continuity Planner with Designated Leadership | Reconstitution Planning Team template (WORD)
|  | ● Identify, train, and exercise building damage assessment and recovery team | Continuity Planner with Designated Leadership
|  | ● Establish and enter into memorandums of understanding/memorandums of agreement (MOU/MOA) | Senior Leadership
|  | ● Conduct training and exercises for continuity/reconstitution personnel | Continuity Planner
|  | Plan for each reconstitution level established to support the planning process and focus the level of effort based on the situation. Reconstitution planning levels have been created to focus and support the reconstitution planning process; a description of the levels is provided below: | Reconstitution Leader with Reconstitution Planning Team
|  | 1. Reconstitution Level 1 (Operational Planning): The primary operating facility has suffered no damage or has been minimally damaged. Planning for this level of disruption focuses on returning operations to the primary operating facilities, which includes restoring normal operations with personnel, records, and equipment at the primary operating facility once the threat or disruption has ended. This level generally would last less than 30 days. | Reconstitution Leader with Reconstitution Planning Team | Reconstitution Operation Plan Checklist - Level 1 (Tab 1) (Excel)
|  | 2. Reconstitution Level 2 (Short Term Planning): The primary operating facility has been moderately damaged. Planning for this level of disruption focuses on moving operations to a temporary operating facility, which includes restoring normal operations with personnel, records, and equipment at a temporary operating facility. This level generally would last from one to six months. | Reconstitution Leader with Reconstitution Planning Team | Reconstitution Short Term Plan Checklist - Level 2 (Tab 2) (Excel)
|  | 3. Reconstitution Level 3 (Long Term Planning): The primary operating facility has been severely damaged or damaged beyond repair. Planning for this level of disruption focuses on moving operations to a new or rebuilt operating facility, which includes restoring normal operations with personnel, records, and equipment at a new or rebuilt operating facility. This level generally will last six months or longer. | Reconstitution Leader with Reconstitution Planning Team | Reconstitution Long Term Plan Checklist - Level 3 (Tab 3) (Excel)
TEST, TRAINING AND EXERCISES (TT&E)
|  | 1. Develop and maintain a continuity Test, Training and Exercises (TT&E) program that identifies the components, processes, and requirements for the training and preparedness of personnel needed to support the continuation of the performance of essential functions | Continuity Planner | In implementation of this TT&E: - Document all conducted TT&E events, including recording the date of the event, those participating in the event, and the results of the event; - Utilize an all-hazards approach to demonstrate the viability of their continuity plans and programs; |  | 2
TESTING: Testing a system ensures that it works as intended. Tests need to be completed at least annually for all systems and procedures included in the continuity plan, following the timelines specified in FCD 1 and CGC 2. The planning team needs to verify that a system will be functional from the designated continuity facility. It is recommended that alert and notification procedures be tested at least monthly because of changes in personnel.
|  | TRAINING: An organization's training program should include and document annually: | Continuity Planner
|  | a. ALL AGENCY PERSONNEL. All agency personnel should be provided a clear understanding of the agency's continuity plans and the roles and responsibilities of its employees. | Continuity Planner | All employee will receive the following training: - Continuity awareness briefings or other means of orientation for the entire workforce. Note that the Annual Training Seminar described in line 146 fulfills this requirement.
|  | b. LEADERSHIP TRAINING. | Continuity Planner | Training tailored for the organization's leadership should include: - Annual training on their agency's essential functions, including training on their continuity responsibilities; - Annual training for all personnel designated within the orders of succession for Organization Head or other key positions who assume the authority and responsibility of the organization's leadership if that leadership is incapacitated or becomes otherwise unavailable during a continuity activation; - Annual training for officials listed within the delegations of authority on all pre-delegated authorities for making policy determinations and other decisions; - Periodic briefings to managers about the essential records program and its relationship to their essential records and business needs.
|  | c. ERG TRAINING. Training for ERG members should ensure attainment of a desired threshold of knowledge of agency continuity plans and procedures and demonstrated capability to continue their agency's essential functions. | Continuity Planner | ERG and DERG members and other designated continuity personnel should receive: - Annual briefings for ERG and DERG on organization continuity and devolution plans that involve using, or relocating to, continuity facilities, existing facilities, or other work arrangements, such as telework; - Annual training on the activation of continuity plans, including unannounced relocation to alternate sites, to include telework options, and devolution of operations to devolution sites; - Annual training for ERG and DERG members on the capabilities of communications and IT systems to be used during a continuity or devolution event; - Annual training for ERG and DERG members regarding identification, protection, and ready availability of electronic and hardcopy documents, references, records, information systems, and data management software and equipment (including classified and other sensitive data) needed to support essential functions during a continuity or devolution activation; and - Annual training for ERG and DERG members on an organization’s devolution option for continuity, to address how each organization will identify and conduct its essential functions during an increased threat situation or in the aftermath of a catastrophic emergency.
|  | d. EXTERNAL PERSONNEL. Training on the roles and responsibilities for personnel, including host or contractor personnel, who are assigned to activate, support, and sustain continuity and devolution operations. | Designated Agency Leader; Continuity Planner
|  | EXERCISES: An organization's exercise program should include and document annually: |  |  |  | 3
|  | a. ANNUAL TRAINING SEMINAR. Conduct an annual HSEEP-compliant training seminar for all agency personnel to provide them familiarity with the agency's continuity plans and procedures to continue its essential functions. | Continuity Planner |  |  | 4. Continuity personnel
|  | b. WEBINAR FOR NEW HIRES. Based on the annual HSEEP-compliant training seminar, create a webinar on the Agency's Continuity Plan to ensure all new personnel are made aware of the agency's continuity plans during initial in-processing. | Continuity Planner and Human Resources
|  | c. QUARTERLY ALERT/NOTIFICATION DRILLS. Conduct quarterly testing of alert, notification, and activation procedures for continuity and devolution personnel and personnel at the organizations HQ. | Designated Agency Leader, ERG Team facilitated by Continuity Planner | During these Drill, conduct: - Quarterly testing of the internal and external interoperability and viability of communications equipment and systems; - Inspection of "Drive Away" kits of ERG team members
|  | d. TABLETOP EXERCISE FOR LEADERS. | Senior Leadership facilitated by Continuity Planner | Conduct Tabletop Exercise using a continuity event scenario to assess plan, policies and leadership decision associated with implementation of the agency continuity plan
|  | e. FULL SCALE EXERCISE (FSE). Conduct an annual Full-Scale Exercise (for Continuity personnel) of the capabilities required to perform an organization's essential functions, as identified in the BPA. | Exercises to Involve: Exercise Director; Designated Agency Leader; Alternate Facility Personnel; Reconstitution Team; Evaluators; Continuity Planner | During this Full-Scale Exercise conduct the following: - Incorporate the deliberate and preplanned movement of ERG members to an alternate site; - Demonstrate ERG and DERG's understanding of and ability to perform their assigned roles and responsibilities through participation in their organization's continuity TT&E program; - Demonstrate internal and external communications capabilities; - Demonstrate that backup data and records required to support essential functions at alternate sites are sufficient, complete and current; - Annual testing of Recovery strategies for essential records (both classified and unclassified), critical information systems (both classified and unclassified), services, and data; - Annual testing of capabilities for protecting essential records and information systems (both classified and unclassified) and for providing access to them from the continuity facilities; - Annual testing of primary and backup infrastructure systems and services, such as power, water, and fuel, at continuity facilities. - Annual testing and exercising of required physical security capabilities at continuity facilities; - Annual exercise of internal and external interdependencies identified in the organization's continuity plan, with respect to performance of an organization's and other organizations' essential functions; and - Annual testing and telework capabilities, to include IT infrastructure, required to support telework options during a continuity event.
|  | f. RECONSTITUTION EXERCISE. A biennial exercise for ERG members to demonstrate their familiarity with the reconstitution procedures | Exercise Director; Reconstitution Team; Evaluators; Continuity Planner | This exercise can be integrated as part of the annual Continuity Full Scale Exercise (FSE)
|  | g. DEVOLUTION EXERCISE. A biennial exercise for DERG members to demonstrate their familiarity with devolution procedures. | Continuity Planner, Designated Leadership; DERG | Only if devolution is an accepted strategy to ensure the continuity of the agency's essential functions
|  | HOTWASH. Following each exercise, conduct a comprehensive debriefing or Hotwash | Exercise Director
|  | EVALUATIONS. In accordance with HSEEP, incorporate exercise evaluations, AARs, and lessons learned into the development and implementation of a Corrective Action Plan (CAP) | Exercise Director, Evaluators, Continuity Planner | Use a Corrective Action Plan (CAP) to assist in documenting, prioritizing, and resourcing continuity issues across all continuity elements identified during TT&E, assessments, and emergency operations. The CAP should: a. Identify continuity deficiencies and a timeline for corrective action b. Provide responsibilities and a timeline for corrective actions
FINAL PLAN COORDINATION
|  | Fill out Continuity Plan Crosswalk for Agency Continuity Plan | Continuity Planner
|  | Coordinate Agency's Continuity Plan internally with section leaders | Section/Dept. Chiefs and Continuity Planner
|  | Amend plan based on input from Agency leadership | Continuity Planner
|  | Submit signed MOA to Texas Facilities Commission | Continuity Planner
|  | Submit Agency Continuity Plan for signature (Promulgation Statement) | Continuity Planner and Senior Leadership
|  | Distribute and fill out Record of Distribution | Continuity Planner
PLAN SUSTAINMENT
| Annual– Sep 1 | Update ERG Team | Section/Dept. Chiefs and Continuity Planner | Amend appendices to COOP Plan Update alert/notification roster
| Annual– Sep 1 | Update Vendor Contact List | Section/Dept. Chiefs and Continuity Planner | Amend appendices to COOP Plan
| Annual- Sep 1 | Update Organization Chart | Continuity Planner | If there are changes in leadership, make appropriate changes in the Orders of Succession and the Delegations of Authority
| Annual- Sept 1 | Record all changes in the “Record of Changes” document change table | Continuity Planner | Located in COOP Plan
Note on A13: Essential Functions: A subset of government functions that are determined to be critical activities. These essential functions are then used to identify supporting tasks and resources that must be included in the organization’s continuity planning process. The term “essential functions” refers to those functions an organization must continue in a continuity situation, whether they are STTEFs, MEFs, or Essential Supporting Activities.
Note on C15: Mission Essential Functions (MEFs): The limited set of organization-level functions that must be continued throughout, or resumed rapidly after, a disruption of normal activities.
Note on E15: Primary Mission Essential Functions: Those organization MEFs, which must be performed in order to support the performance of Texas Essential Functions, before during and in the aftermath of an emergency. PMEFs need to be continuous or resumed within 12 hours after an event and maintained for up to 30 days or until normal operations can be resumed.
Note on A19: Emergency Relocation Group: Staff assigned responsibility to continue essential functions from an alternate site in the event that their primary facilities are threatened or have been incapacitated by an incident.
Note on C20: Emergency Relocation Group (ERG): Staff assigned responsibility to continue essential functions from an alternate site in the event that their primary facilities are threatened or have been incapacitated by an incident.
Note on C26: Activation: The implementation of a Continuity Plan, whether in whole or in part.
Note on C27: Drive Away Kit: A kit prepared by, and for, an individual who expects to deploy to an alternate site during an emergency. The kit contains items needed to minimally satisfy an individual's personal and professional needs during deployment, such as clothing, medications, a laptop, and other necessities.
Note on E28: DERG: Devolution Emergency Relocation Group
Note on A29: Business Process Analysis: A method of examining, identifying, and mapping the functional processes, workflows, activities, personnel expertise, systems, data, interdependencies, and facilities inherent in the execution of a function or requirement.
Note on C30: Business Process Analysis: A method of examining, identifying, and mapping the functional processes, workflows, activities, personnel expertise, systems, data, interdependencies, and facilities inherent in the execution of a function or requirement.
Note on E30: NOTE: When documenting the BPA results, it may be useful to think of the BPA data sheet as a guide that can be used by back up personnel who may be filling in for the personnel who normally perform the function but are not available as a result of the disruption. The BPA data sheet may also be useful for new senior leadership to more fully appreciate the complexities and interdependencies inherent in accomplishing some Mission Essential Functions
Note on E38: Memorandum of Agreement/Memorandum of Understanding: Written agreements between organizations that require specific goods or services to be furnished or task to be accomplished by one organization in support of another.
Note on A40: Business Impact Analysis: A method of identifying the effects of failing to perform a function or requirement.
Note on C41: Business Impact Analysis: A method of identifying the effects of failing to perform a function or requirement.
Note on A49: Based on the BIA results, Agency evaluates the risk to the performance of each individual MEF and determines how to address unacceptable threats and vulnerabilities.
Note on C59: Alternate Facility: "Alternate sites" are locations, other than the primary facility, used to carry out essential functions by relocating ERG members following activation of the Continuity Plan. These sites refer to not only other facilities and locations, but also work arrangements such as telework and mobile work concepts.
Note on E60: 1. Hot site: A facility that already has in place the computer, telecommunications, other information technology, infrastructure, and personnel required to recover essential functions. 2. Warm site: A facility that is equipped with some computer, telecommunications, other information technology, and environmental infrastructure, which is capable of providing backup after additional personnel, equipment, supplies, software, or customization are provided. 3. Cold site: A facility that is not manned on a day-to-day basis by personnel from primary operating facility. Organizations may be required to pre-install telecommunication equipment and IT infrastructure upon selection/purchase and deploy designated IT essential personnel to the facility to activate equipment/systems before it can be used.
Note on C63: Memorandum of Agreement/Memorandum of Understanding: Written agreements between organizations that require specific goods or services to be furnished or task to be accomplished by one organization in support of another.
Note on A67: Devolution requires the transition of roles and responsibilities for performance of essential functions through pre-authorized delegations of authority and responsibility. The authorities are delegated from an organization's primary operating staff to other employees internal or external to the organization in order to sustain essential functions for an extended period. Devolution is a continuity option instead of, or in conjunction with, relocation in order to ensure the continued performance of essential functions.
Note on C68: Devolution requires the transition of roles and responsibilities for performance of essential functions through pre-authorized delegations of authority and responsibility. The authorities are delegated from an organization's primary operating staff to other employees internal or external to the organization in order to sustain essential functions for an extended period. Devolution is a continuity option instead of, or in conjunction with, relocation in order to ensure the continued performance of essential functions.
Note on E79: STTEFs: State, Territorial, Tribal Essential Functions
Note on A80: Essential Records. "Essential Records" refers to information systems technology, applications, and infrastructure, electronic and hardcopy documents, references, and records needed to support the continued performance of essential functions during a continuity activation. Information that is needed for the resumption of normal operation for reconstitution should also be protected.
Note on C81: Essential Records. "Essential Records" refers to information systems technology, applications, and infrastructure, electronic and hardcopy documents, references, and records needed to support the continued performance of essential functions during a continuity activation. Information that is needed for the resumption of normal operation for reconstitution should also be protected.
Note on A83: Orders of Succession: Orders of Succession are a formal, sequential listing of organization positions (rather than specific names of individuals) that identify who is authorized to assume a particular leadership or management role under specific circumstances.
Note on C84: Orders of Succession: Orders of Succession are a formal, sequential listing of organization positions (rather than specific names of individuals) that identify who is authorized to assume a particular leadership or management role under specific circumstances.
Note on A95: Delegations of Authority: Identification by position of the authorities for making policy determinations and decisions at Headquarters, regional and field levels, and all other organizational locations. Generally, pre-determined delegations of authority will take effect when normal channels of direction have been disrupted and will lapse when these channels have been reestablished.
Note on C96: Delegations of Authority: Identification by position of the authorities for making policy determinations and decisions at Headquarters, regional and field levels, and all other organizational locations. Generally, pre-determined delegations of authority will take effect when normal channels of direction have been disrupted and will lapse when these channels have been reestablished.
Note on C102: Devolution Emergency Response Group (DERG): Personnel stationed at the Devolution Site who are identified to conduct essential functions.
Note on E102: Devolution Emergency Response Group (DERG): Personnel stationed at the Devolution Site who are identified to conduct essential functions.
Note on A120: Reconstitution: The process by which surviving and/or replacement organization personnel resume normal organization operations from the original or replacement primary operating facility.
Note on C121: Reconstitution: The process by which surviving and/or replacement organization personnel resume normal organization operations from the original or replacement primary operating facility.
Note on A133: Tests, Training, and Exercises: Measures to ensure that an organization's continuity plan is capable of supporting the continued execution of the organization's essential functions throughout the duration of a continuity event. TT&E activities are designed to familiarize, impart skills and ensure viability of continuity plans.
Note on C134: Tests, Training, and Exercises: Measures to ensure that an organization's continuity plan is capable of supporting the continued execution of the organization's essential functions throughout the duration of a continuity event. TT&E activities are designed to familiarize, impart skills and ensure viability of continuity plans.
Note on C142: Homeland Security Exercise and Evaluation Program (HSEEP): HSEEP is a capabilities based and performance-based program that furnishes standardized policies, doctrines, and terminologies for the design, development, performance and evaluation of homeland security exercises. HSEEP also provides tools and resources to facilitate the management of self-sustaining homeland security exercise program.
Note on E150: Corrective Action Program – An organized method to document and track improvement actions for a program. The Corrective Action Program (CAP) system is a web-based tool that enables Federal, State, and local emergency response and homeland security officials to develop, prioritize, track, and analyze corrective actions following exercises or real world incidents. Users may enter data from a finalized After Action Report/Improvement Plan, track the progress of corrective action implementation, and analyze and report on trends in improvement plans.

## likelihood threat
Likelihood of Threat or Hazard Occurrence
Value | Likelihood of Threat Occurrence
9 – 10 | Extremely Likely – Certainty - Happens often
7 – 8 | Highly Likely – Happens occasionally
5 – 6 | Probable – Happened before; More than once
3 – 4 | Possible – Happened many years ago
1 – 2 | Unlikely – No recent memory of this happening
0 | Does not happen
Reference: FEMA, Continuity Guidance Circular 2 (CGC 2), Continuity Guidance for Non-Federal Governments: Mission Essential Functions Identification Process (States, Territories, Tribes, and Local Government Jurisdictions), FEMA P-789, October 2013, Annex D, pg. D-5

## vulnerabilities
Mission Essential Functions (MEF) Vulnerability Value
Numeric Value | Value Description
10 Critically High | Exceptionally grave vulnerability to mission performance
9 Extremely High | Grave vulnerability, where negative effect results in delays to mission for an extended period of time.
8 Very High | Serious vulnerability, where negative effect results in delays to mission for a limited period of time.
7 High | Serious vulnerability, where the negative effect results in minor mission delays.
6 Medium High | Moderate to serious vulnerability, where the negative effect results in slight mission delays.
5 Medium | Moderate vulnerability, where the negative effect results in no impact to mission completion.
4 Medium Low | Minimal vulnerability, where negative effect results in no impact to mission completion
3 Low | Minimal vulnerability of consequence without long term negative effects.
2 Very Low | Negligible vulnerability of consequences with minimal long term negative effects.
1 Extremely Low | Negligible vulnerability of consequences with no long term negative effect.
0 Non existent | No vulnerability.

## failure
MEF Failure Impact Value
Threat and Hazard Impact Value
Numeric Value | Value Description
10 Critically High | Exceptionally grave impact preventing mission performance.
9 Extremely High | Grave impact requiring corrective action and negative effect results in delays to mission for an extended period of time.
8 Very High | Serious impact requiring corrective action and negative effect results in delays to mission for a limited period of time.
7 High | Serious impact requiring corrective action, where the negative effect results in minor mission delays.
6 Medium High | Moderate to serious impact requiring corrective action, where the negative effect results in slight mission delays.
5 Medium | Moderate impact requiring corrective action, where the negative effect results in no impact to mission completion.
4 Medium Low | Minimal impact requiring corrective action, where negative effect results in no impact to mission completion.
3 Low | Minimal impact or consequence without long term negative effects.
2 Very Low | Negligible consequences or impact with minimal long term negative effect.
1 Extremely Low | Negligible consequences or impact with no long term negative effect.
0 Non existent | No consequences.

## records inventory
Essential Records Inventory
Essential File, Record, or Database | Support to Essential Functions | Form of Record (e.g., hardcopy, electronic) | Pre-positioned at Continuity facility | Hand Carried to Continuity facility | Multiple Storage location(s) Y/N | Maintenance Frequency